## Sheet1
ت | الهدف | مسؤولية البعثة | مسؤولية الوزارة | المتابعة | الاجراء المتخذ | المقترحات | القرار
1 | السياسة والاسترتيجية | العقيد جيسز دايفز | مديرية التخطيط | تم تشكيل فريق لاجراء المتابعة للاستراتيجية من كافة الجهات | لم يتم تزويدنا باخر المستجدات | تزويدنا بخطة متابعة وتقييم تنفيذ الوثائق الاستراتيجية متضمنة توقيتات المراجعة الدورية | دائرة العمليات مديرية التخطيط
2 | التخطيط الدفاعي | العقيد جايس دايفز | مديرية التخطيط | لازالت الورش مستمرة بالانعقاد لاكمال السيناريوهات | لاتوجد لدينا خطة هذه السنة من الورش | بعثة الناتو في العراق تزويدنا بمواعيد الورش والمشتركين بها | بعثة الناتو في العراق
3 | الموارد البشرية | العقيد تيمير بيلاس | دائرة الادارة مع للافراد مديرية نظم المعلومات | لازال العمل مستمر بالتوصيف الوظيفي والعمل متلكؤ مع الشركة المجهزة للنظام | تم تزويدنا باخر المستجدات | يجب ان يتم العمل بصورة اكثر دقة وسرعة من قبل كافة الجهات وبالتعاون والتنسيق مع اللواء
4 | الامن السبراني | المقدم مانويل كيفاس | مديرية الامن السبراني | العمل مستمر في المديرية بتخصيص كوادر فنية وبالتدريب مع بعثة الناتو | المتابعة مع المديرية في كافة النواحي من خلال اللواء وليد مستشار الامن السبراني في راج | نحتاج ان تكون رؤية رئاستنا بان تكون هذه المديرية كاساس لبناء جديد وفق معايير الناتو من كافة النواحي كونها جديدة | مقترح
5 | الدعم اللوجستي | المقدم ستو فيلد | دائرة الميرة | العمل مستمر في نظام الناتو للترميز وهناك مشكلة مع الشركة المجهزة للنظام الخاص بالمستودعات ولازالت استراتيجية الدعم اللوجستي لم يتم اقرارها لحد الان. | المتابعة مستمرة في نشر نظام الترميز في القيادات والمديريات وتدريب الافراد على النظام وارسالهم في دورات بالتنسيق مع بعثة الناتو | اقرار استراتيجية الدعم اللوجستي ومتابعة العمل مع الشركة المجهزة للنظام ومتابعة خطة اكمال نظام الترميز بالتعاون مع الناتو | دائرة الميرة المتابعة مع دائرة العمليات
6 | بناء النزاهة | مارجا هوفس | المفتشية العسكرية العامة | العمل مستمر في تقرير المقابلات بالاضافة الى استراتيجية الفساد من خلال اللقاءات والورش لوضع الاسس الصحيحة للعلاقة بين الاطراف المشتركة | تم استلام التقرير للنظراء وتقديمه الى السيد وزير الدفاع يتم متابعة العمل بين الادعاء العام والمفتش العسكري والاستخبارات لتحديد الية العمل المشترك في بناء النزاهة | العمل يسير وفق ما مخطط اليه لاتوجد مقترحات بصدد الهدف
7 | ادارة منظومة التدريب | العقيد ايد فن دي بوسبورت | دائرة التدريب / التدريب العسكري | تجري العملية وفق ما مخطط لها بالرغم من وجود بعض الصعوبات والتحديات في اصدار الاوامر الادارية وبعض الاحيان الغاء الدورة من قبل الناتو او تاخير في ارسال الدعوات من قبلهم | الاستمرار بالعمل وتخويل الصلاحيات لتقليل الاجراءات وهذا يتطلب ان تكون هناك ثقة كبيرة بين المراجع والدوائر المرؤوسة | يتم العمل حاليا من قبل امانة سر التدريب في امانة السر العام على وضع برنامج يتم تنصيبه في شبكة وزارة الدفاع وتتمكن كافة الجهات المعنية من دائرة التدريب ومديرية التدريب العسكري وامانة سر التدريب في راج وفي امانة السر العام من متابعة الدعوات والفعاليات التدريبية التي تجري في خارج العراق اول باول بالاضافة الى التدقيق الامني | دائرة التدريب مديرية التدريب العسكري امين سر العلاقات الدفاعية راج امين سر التدريب امانة السر العام
8 | مدارس الصنوف والخدمات | العقيد جورج فيرر | دائرة التدريب معظم الدوائر وبعض القيادات | لايوجد تحديث ولكن العمل مستمر مع 15 مدرسة مختلفة | تتابع دائرة التدريب العمل مع الناتو الا انه عمل متشعب وواسع | تقديم دراسة مشتركة بين الجهات كافة وبرئاسة دائرة التدريب لوضع نظام متابعة الاعمال التي تجري وماهي النتائج لهذه الاعمال المنفذة في كل مدرسة ومدى الفائدة منها وجدوتها | دائرة التدريب عرض الخطة
9 | منظومة ضباط الصف | ر ع بوب بيلدجاك | دائرة التدريب | لم تبصر النور الاستراتيجية التي من المفترض ان يتم ماقشتها عدة مرات | دائرة التدريب قامت بعرضها ومناقشتها مع الجميع ولكن لازالت العملية متعثرة باصدارها | نقترح ان يتم اتخاذ القرار بصدد اقرارها من قبلكم شخصيا لان الموضوع اتخذ مسارا طويلا ووقت اطول | دائرة العمليات دائرة التدريب
10 | ادارة الازمات | المقدم فيتو سميرلي | دائرة الاسناد الهندسي/ مديرية الشؤون العسكرية للاغراض المدنية | تم تبديل مدير الشؤون العسكرية للاغراض المدنية مما سبب ارباك بالعمل | المديرية بحاجة الى ان يكون كادرها ممن لديهم الخبرة ومزيد من التدريب والالمام بسياقات العمل التي تتبعها الناتو | تشكيل لجنة لدراسة واقع المديرية وتقديم المقترحات التي ترتقي باداء المديرية | دائرة الاسناد الهندسي
11 | تطوير المناهج واعضاء الهيئات التدريسية | العقيد ريتش ريسايث | جامعة الدفاع للدراسات العسكرية | كافة الكليات والمؤسسات | تعمل الجامعة من خلال مقرها وكافة المؤسسات التابعة لها بالتنسيق والعمل المستمر مع مستشاري بعثة الناتو في العراق على تنقيح المناهج بصورة مستمرة بالإضافة الى تطوير الكوادر التعليمية من خلال ورش العمل والدورات التطويرية وزيارات مؤسسات في مختلف دول العالم للاطلاع على اخر المستجدات | تقوم الجامعة بارسال تقارير فصلية بتطوير العمل في المناهج والهيئات التعليمية والتدريسية بتوقيتات محددة وبتفاصيل دقيقة ليتسنى متابعة العمل بصورة ادق | جامعة الدفاع للدراسات العسكرية عرض الخطة
12 | شؤون المراة | السيدة هانرييتا حونسون | السيدة سهيلة قسم المراة مديرية حقوق الانسان | عقدت عدة ورش عمل في قيادات الاسلحة وبصدد اكمال خطة العمل السنوية | تحتاج الى تعديل في ملاكاتها بالاضافة الى التعاون والتنسيق مع المؤسسات الاخرى لاغراض اكمال خطتها السنوية ووضع استراتيجية عمل للقسم وتطوير الاداء | تم اصدار امر الى دائرة العمليات لتعديل ملاك القسم بالاضافة الى الجامعة لغرض تطوير مناهج التدريب بحاجة الى قيام القسم بمراجعة مديرية التنظيم والتنسيق مع الجامعة | الدائرة القانونية دائرة العمليات متابعة الملاك مـــــع مديرية التنظيم
13 | الهياكل التنظيمية والقيادية | العقيد جوس مينولو | مديرية التنظيم | الهدف منذ بدايته ولحد اللحظة لازال متغير الوصف بصورة مستمرة بسبب تعقيداته كونه يتعامل مع القيادة والسيطرة والتي متغيرة بسبب التطورات العسكرية والسياسية | متابعة عمل الهياكل التنظيمية مع مديرية التنظيم وفق الاحتياجات التي تلبي متلطباتها | العمل مستمر وفق خطة العمل الموضوعة من قبل البعثة بالتعاون والتنسيق مع مديرية التنظيم | دائرة العمليات مديرية التنظيم
14 | الاستخبارات | العقيد اليكس هاريس | امين سر الاستخبارات امانة السر العام | تم اكمال الاستراتيجية وهي في طور المصادقة | متابعة مصادقتها | بعد المصادقة عليها ينبغي وضع خطة عمل لاجراءات التنفيذ من قبل فريق عمل مشترك لغرض تنفيذها | العمل على إكمال خطة تنفيذ الإستراتيجية
15 | المشبهات | المقدم اندريس فاكس | مركز وسائل الايضاح | العمل مستمر مع مركز وسائل الايضاح لغرض الارتقاء بالعمل وصياغة استراتيجية خاصة بالمشبهات | تم ارسال مدير المركز وضباط لغرض الاطلاع على المشبهات وعملها في ايطاليا | المتابعة مع مدير المركز لوضع رؤية لاستراتيجية المشبهات وصياغتها بالتعاون مع بعثة الناتو وترك موضوع تصنيع المشبهات فهذا ليس واجب المركز | دائرة التدريب
16 | القنون الدولي الانساني وحقوق الانسان | لايوجد مستشار في البعثة حاليا بسبب اجراءات الفيزا ولكن البديل ادى الواجب وبصورة جيدة | مديرية حقوق الانسان الدائرة القانونية | العمل مستمر في موضوع اضافة القانون الدولي الانساني في المناهج بالاضافة الى تثقيف المشاورين القانونيين في قيادات الأسلحة والدوائر بالموضوع ولجنة الخبراء يتم العمل على تطويرها من خلال ورش العمل والدورات وبطاقة الجندي يتم العمل على نشرها بين صفوف القوات المسلحة | متابعة مستمرة لاستثمار الجهود في توزيع بطاقة الجندي بالاضافة الى متابعة البعثة لتطوير لجنة الخبراء | متابعة العمل مع البعثة ومديرية حقوق الانسان والدائرة القانونية للارتقاء بالاداء | الدائرة القانونية
17 | حماية المدنيين | الانسة ايستر كرسنيتش | الفريق الركن سمير عبد الكريم | تم كتابة استراتيجيتان واحدة من قبل مديرية التخطيط وهي لا تتلائم مع متطلبات الناتو والاخرى كتبت من قبل بعثة الناتو وقد ادرجت كافة الاهداف التي ضمنت في استراتيجية مديرية التخطيط | العمل جاري حاليا على وضع الملاحظات من قبل قيادات الاسلحة والمديريات المعنية باشراف دائرة الاسناد الهندسي ورئاسة اركان الجيش بالمتابعة اكمال كافة الملاحظات تم طلب الحصول على استراتيجية حماية المدنيين الصادرة من رئاسة الوزراء من قبل مستشارية الامن القومي | يتم عرض كلا الاستراتيجيتين في ورشة عمل للخروج باستراتيجية موثوقة ومتقنة ومعتمدة | عند ورود الإستراتيجية تعقد ورشة عمل في مديرية التخطيط لمناقشة كافة الاستراتيجيات
18 | كفاءة اللغات | السيد جيرمي نورس | دائرة التدريب ومعهد اللغات العسكري | تم ارسال العديد من المدرسين لغرض تطوير ادائهم بالاضافة الى تطوير المناهج وعمل قيادات الاسلحة لاجل تطوير قدرات المنتسبين في مجال اللغة الانكليزية | العمل مستمر بكافة المستويات للارتقاء بتطوير اللغة الانكليزية بين منتسبي الوزارة من المدنيين والعسكريين | الاستمرار بالمتابعة مع اجراءات دائرة التدريب ومعهد اللغات العسكري لاجل الارتقاء باداء المنتسبين في مجال اللغة الانكليزية | دائرة التدريب جامعة الدفاع للدراسات العسكرية (معهد اللغات)
19 | التوافق مع سياقات الناتو | السيد رانزي دي فيرز | اللواء الركن ياسر واللواء الركن نصر | فكرة القدرات العملياتية. تم تعيين فريق عمل من رئاسة اركان الجيش ودائرة التدريب للاشراف على تخصيص سرية من فرقة القوات الخاصة وفي المرحلة الاولية من اختيار الافراد للسرية وانتظار الموافقات فريق التخطيط الاساسي تم اجراء العديد من ورش العمل والمؤتمرات بالاضافة الى المشاركات في تطوير القابليات في مؤسسات الناتو المختلفة الاصولية للبدء بالبرنامج. | فكرة القدرات العملياتية العمل مستمر من قبل مستشار البعثة مع فريق العمل من الوزارة والتقدم ببطء ولكن بخطوات مدروسة . فريق التخطيط الاساسي استمرارية العمل ومشاركة بعض اعضاء الفريق في تمرين الاسد المتأهب في الاردن على ان يكونوا ضمن فريق التخطيط للتمرين سيعطي زخم كبير وخبرة في مجال التخطيط للتمارين | تقديم الدعم لكل الفرق العاملة في كلا المحورين ودعم مستشار بعثة الناتو بالاضافة الى الحاجة الى تعيين ضابط من رئاسة اركان الجيش ليكون مراقب على فريق التخطيط الاساسي ونقترح ان يكون اللواء الطيار الركن سليم عبد الحميد | كتابة مطالعة ومتابعة الموضوع
20 | الجاهزية | العقيد سليفيو ماردي | هيئة الجاهزية | الهدف جديد وبحاجة الى تفعيل كلتا الجهتين من جهة الوزارة والبعثة | تم وضع خطة للعمل ولكن هناك تقارير ينبغي عدم تزويدها الى بعثة الناتو في العراق حسب اوامر السيد رئيس اركان الجيش المحترم بسبب السرية ولكون هنالك ضباط من تركيا ضمن البعثة | نحتاج الى تبليغ بعثة الناتو في العراق على تزويدنا بافضل طرق لعرض الجاهزية وطريقة عرض التقارير بالاضافة الى ايجاد حل لمشكلة السرية وعدم تزويدهم باي تقارير في المستقبل. | متابعة هيئة الجاهزية
21 | استراتيجية الاعلام | السيدة ديزي ديسوفي | مديرية الاعلام والتوجيه المعنوي | العمل يجري بين البعثة ومديرية الاعلام لغرض وضع الية عمل لصياغة استراتيجية اعلام رصينة تلبي متطلبات وزارة الدفاع | قامت بعثة الناتو في العراق بتقديم خطة عمل سنوية مع مديرية الاعلام وهي في طور المناقشة والمتابعة | متابعة العمل مع الجميع كون الهدف جديد والعمل في بدايته | متابعة

## Sheet2
CRC ACTION TRACKER | [12 empty] | Update: | 2024-05-24
LTO NO. | LTO address | NMI advisor | MOD | Follow up | Action | Suggestions | Decsion | details | DETAILS OF FOLLOW-UP ACTION REQUIRED / TAKEN | REF | SUPPORT / ADVISE | DATE TASKED | FOLLOW-UP DATES | COMMENT
LTO 1 | Policy and Strategy | OF-5 Davies | DCOS OPS / M5 | A team has been formed to conduct follow-up to the strategy from all sides | we get nothing till now | Provide us with a plan to follow up and evaluate the implementation of strategic documents, including the timing of the periodic review | DCOS Ops & M5 give us last update | M5 / DCOS OPS to report on the implementation of the Military Strategy. | M5 / DCOS OPS to: 1) Establish implementation team 2) Report on the implementation of the Military Strategy and the revision of the Defence Planning Guide on a monthly basis. 3) Assess implementation at Service Comds and alignment to service specific operational planning. | CHOD Assessment Board DEC 2023 COM/CHOD 10FEB24 | OF-5 Davies | 2024-02-24 | Monthly | M5 / DCOS OPS must do monthly workshops with NMI to follow-up progress of Strategy implementation. Also brief on the plan for undertaking the refresh of the Military Strategy now the National Security Strategy and the new Security Sector Reform programme have been published. It is CHODs direction to give presentation of the developed Strategies over the past three years for subsequent National Security Agency presentation.
LTO 2 | Defense Planning | OF-5 Davies | DCOS OPS / M5 | The workshops are still continuing to be held to complete the scenarios | weneed to get the whole plans for all workshops will be helding this year | DCOS Ops / M5 + NMI provide us with all the schduale of the workshops | DCOS Ops & M5 give us last update | M5 to support and manage Defence Planning Workshops together with NMI. | NMI and M5 team to present the 2024 Defence Planning Workshop plan and content to LNO and GENSEC. | CRC MAR 24 | OF-5 Davies | 2024-03-24 |  | On-going workshops.
LTO 3 | Humen Resuores | OF-5 Belas | DCOS Admin + DG Personal + CIO | Work is still continuing with job descriptions and work is lagging with the company that equipped the system | We get weekly reports from DCOS Admin , Nothing from DG Personal same for CIO | Work must be done more accurately and quickly by all parties and in cooperation and coordination with the brigade Waleed from CHOD | Follow up with DCOS Admin and with OSC I about the company to deliver the system | M5 / DCOS OPS must provide M1 with details to be integrated into the Human Ressources Management strategy/policy. DCOS ADMIN / M1 to follow-up the development of Jobdescriptions at Service Commands. DCOS ADMIN / M1 to follow-up the development of Jobdescriptions at Service Commands. | Track and report on implementation of: 1) job descriptions, 2) performance evaluations and 3) talent management programs. | CHOD Assessment Board DEC 2023 and JAP Review JAN24 | OF-5 Belas | Dec 23 / Jan 24 |  | HRM proces supported by legacy IT system.
LTO 4 | Cyber Security | OF-5 Jones | DCOS OPS / CSD | Work continues in the Directorate by allocating technical cadres and training with the NATO mission | Follow-up with the Directorate in all aspects through Major General Walid, Cyber Security Advisor at the Army Chief of Staff | We need the vision of our presidency to be this directorate as a basis for a new building according to NATO standards in all respects because it is new Directorate | Informed NMI advisor and CSD to work togeather for new stracture organization and it should be inropibilty with NATO. CRC May 2024 | 1) DCOS OPS to update on establishing the Cybersecurity Directorate (CSD). | Work continues to allocate technical personel and training. | Ninth Meeting 2023 and CHOD Assessment Board DEC 2023 CRC JUN24 | OF-5 Jones | 2024-12-23 |  | Briefed at CRC 4. JUN 2024 by DIR CSD. The Cybersecurity Directorate will amend the staffing and organizational structure together with M9, taking into account difficulties in allocating staff. The expansion should be gradual and phased in accordance with a long-term strategic plan. The Cybersecurity Directorate will prepare its own training curricula and deliver it to M7 for inclusion in ATB.
[8 empty] | 2) DIR CSD must visit Service Commands and collect requirements for CSD. |  | CRC MAR 24 | OF-5 Jones | 2024-03-24
[8 empty] | 3) Cybersecurity Directorate must ensure that Cybersecurity goes into the Military Strategy at next review. |  | JAP Review JAN24 | OF-5 Jones | 2024-01-24
[8 empty] | 4) The Cybersecurity Directorate must prepare the Cybersecurity Strategy and establish a Strategy Preparation Committee. | [5 empty] | Must identify the members required to participate in this Committee from the departments and directorates of MOD and consult NMI advisors.
LTO 5 | Logistic Support | OF-4 Jennings | DCOS Log | Work is continuing on the NATO coding system, there is a problem with the company supplying the warehouse system, and the logistics support strategy has not yet been approved. | Follow-up continues in spreading the coding system in the commands and directorates, training individuals on the system and sending them in courses in coordination with the NATO mission | Approving the logistical support strategy, following up the work with the company supplying the system, and following up the plan to complete the coding system in cooperation with NATO | Follow up with DCOS LOG and NMI to present the Logistic Strategy with DCOS Ops ASAP | 1) DCOS LOG to develop a Logistic Strategy and approved by CHOD. |  | CHOD Assessment Board DEC 2023 and JAP Review JAN24 | OF-4 Jennings | Dec 23 / Jan 24
[8 empty] | 2) DCOS LOG to provide implementation plan for Codification System. | The Codification system to be activated among all Service Commands, and personnel selected to support. | JAP Review & CRC MAR 24 | OF-4 Jennings | 2024-03-24
LTO 6 | Building Intigrity | A-4 Hofs | MIG | Work is continuing on the interview report in addition to the corruption strategy through meetings and workshops to lay the right foundations for the relationship between the joint parties | The peers review report was received and submitted to the Minister of Defense. Work is being followed up between the General Prosecution, the Military Inspector and the Intelligence to determine the mechanism of joint action in building integrity. They all agreed about the mechanism and every side get his task. The peer review report delivered from Minister office to the General Prosecution / Directorate of Integrity and Investigation to deal with it. | The NMI advisor working very to ensure the whole interlocotar are working togeather . | follow up with MIG and all sides |  |  |  | A-4 Hofs
LTO 7 | Management Training System | A-5 De Vries | DCOS Training / M7 | The process is proceeding as planned, despite some difficulties and challenges in issuing administrative orders, and sometimes canceling the course by NATO or delaying the sending of invitations by them. | Continuing to work and delegating powers to reduce procedures, and this requires that there be great trust between the references and subordinate departments | Forming a committee of one of the advisors to the Presidency of Staff and the concerned departments and setting controls and delegating powers to reduce and simplify procedures, and this is within the government program of the state | Gen Sec Training published new system. This system will make all parties look at it and each must the action in right time. This system will be installed in MoD network. | DCOS Training to obtain approval from Iraqi Government to participate in NATO Joint Excercises. |  | Second Meeting 2023 | A-5 De Vries
LTO 8 | Schools of Classes and Services | OF-5 Aleman | DCOS Training / SC most of the Directorate |  |  |  |  | M7 to lead Joint study with the 15 schools |  |  | OF-5 Aleman
LTO 9 | NCO strategy | OR-9 Peldjak | DCOS Training / SC most of the Directorate |  |  |  |  | DCOS TRNG/M7 to develop a Non-Commissioned Officer (NCO) strategy and get approved from CHOD. | DCOS TRNG/M7 presented a strategy but awaits approval. | CHOD Assessment Board DEC 2024 JAP Review JAN24 CRC MAR24 | OR-9 Peldjak | Dec 23 / Jan 24; Mar 24 |  | Service Commands give their requirements to the NCO Strategy.
LTO 10 | Crisis Management | OF-4 Samaretti | Directorate of Enigneering Support / MACP | Changing the Director of MACP make some confusing . MoI established Crisis Management Center. | The Directorate needs to have experience, more training and familiarity with NATO's work contexts. | Forming a committee to study the reality of the Directorate and submit proposals that improve the performance of the Directorate | Directorate of Enigneering Support / MACP . CHOD office & NMI advisors | 1) DCOS OPS to establish Crisis Management section and provide a study in each Directorate. |  | Fourth Meeting 2023 | OF-4 Samaretti |  |  | Coordinated with M9.
[8 empty] | 2) Re-organization of the MACP Directorate to CM efforts according to NATO recommendations. | Crisis Management Center to be developed on Strategy for CM. | Sixth and Ninth Meeting 2023 and JAP Review JAN24 | OF-4 Samaretti | 2024-01-24
[8 empty] | 3) DIR MACP to work with Service Commands to develop Crisis Management contingency plans. |  | CRC MAR 24 | OF-4 Samaretti | 2024-03-24 |  | Once plans are written joint exercises must be conducted to train and rehearse those plans.
LTO 11 | OF-5 Forsyth | DUFMS | All Colleges and insistuitions | The university works through its headquarters and all its affiliated institutions in coordination and continuous work with the advisers of the NATO mission in Iraq to revise the curricula on an ongoing basis in addition to developing educational cadres through workshops, development courses and visits to institutions in various countries of the world to see the latest developments | The university sends quarterly reports on the development of work in curricula, educational and teaching bodies at specific times and in accurate details so that the work can be followed up more accurately. |  |  | 1) DUFMS to coordinate delivery of Internet Services to its institutions to facilitate e-learning. |  | Seveth Meeting 2023 | OF-5 Forsyth |  |  | Must address related cost.
[8 empty] | 2) DUFMS to develop educational strategies that align to moderne policy-and plansmaking. | Quarterly reports on strategy development to be presented. | JAP Review JAN24 | OF-5 Forsyth | 2024-01-24
LTO 12 | Wome affairs | A-4 Johansen | Legale Department / Hu,em Rights Directorate - Women Affairs Section | Several workshops were held in arms commanders and are in the process of completing the annual work plan | It needs to be adjusted in its staff in addition to cooperation and coordination with other institutions for the purposes of completing its annual plan and developing a work strategy for the department and developing performance | An order has been issued to the Operations Department to modify the staff of the department in addition to the university for the purpose of developing training curricula The department needs to review the Directorate of Organization and Coordination with the University | Legal Department DCOS Operations Follow-up of new stracture with M9 | Women's Affairs Section and Legal Departement must implement the Iraqi national action plan for WPS based on studies by DCOS Training and DUFMS. | Development of strategy for the Legal Department's work on WPS. | Second and Fourth meeting 2023 and JAP Review JAN24. | A-4 Johansen | 2024-01-24 |  | An analysis is required to identify the requirements for additional staff.
LTO 13 | Organizational and leadership structures | OF-4 Sutclif | DCOS Ops / M9 | The goal since its inception and until the moment is still constantly changing description because of its complexities as it deals with command and control, which is changing due to military and political developments | Follow up the work of the organizational structures with the Directorate of Organization according to the needs that meet its requirements | Work is continuing according to the action plan set by the mission in cooperation and coordination with M9 | DCOS Ops & M9 also the advisor from NMI give us last update | M9 to assure that there are no changes to MOD staff for one-year. | There is a need to follow up on ORG work done at the ORG Directorate (M9). | JAP Review JAN24 | OF-4 Sutclif | 2024-01-24
LTO 14 | Intelligence Strategy | OF-5 Harris | Gen Sec Intill and M2 and DG I&S | The strategy was issued and get approved by MINDAF | Needs to follow up with all parties to estabished Team for follow up the immplementation of the strategy | NMI advisor and CHOD office working togeather to make this happened | NMI & CHOD office | DGIS must develop and get INTEL Strategy approved by CHOD. | Strategy has been completed and in the approval process. | JAP Review JAN24 COM/CHOD 10.FEB24 | OF-5 Harris | 2024-02-24 |  | M5 / DCOS OPS must comment.
LTO 15 | Simulators | OF-5 Lett | DCOS Training and Simulators Center | Work is ongoing with the Simularor Center for the purpose of upgrading work and formulating a strategy for simulators | The director of the center and officers were sent for the purpose of reviewing the simulators and how it is work in Italy | Follow up with the director of the center to develop a vision for the simulators strategy and formulate it in cooperation with the NATO mission and leave the issue of manufacturing simulators, this is not the duty of the center | NMI & DCOS training | 1) DCOS TRNG to describe the requirements for Iraqi Simulation Centers. |  | Second Meeting 2023 | OF-5 Lett
[8 empty] | 2) DCOS TRNG must develop a simulator strategy. | Work is on-going. | Tenth Meeting 2023 | OF-5 Lett |  |  | Must be coordinated with the simulator requirements of the Service Commands, and leverage of Simulator Center knowledge.
[8 empty] | 3) DCOS TRNG to deliver a study on requirements for a Simulator Division in each Service Command. |  | Tenth Meeting 2023 and JAP Review JAN24 | OF-5 Lett | 2024-01-24 |  | In coordination with M9 and DG Personnel.
LTO 16 | International humanitarian law and human rights | A-5 Gundy | Legal Department / Humen Rights Directorate | The advisor not available in the mission currently due to the visa procedures, but Miss. Juleitte did great job and cover the gab in perfect way | Continuous follow-up to invest efforts in distributing the soldier's card. There was a proposal from the mission, funded by the British Embassy, to create an application that could be installed in the solidres phones to put the soldier's card in it. In addition to following up the mission to develop the committee of experts through workshops and sending a group to be TOT for SC and departments | Follow-up work with the mission, the Directorate of Human Rights and the Legal Department to improve performance | Legal Department & NMI Follow-up of what the vision and the POP | 1) Human Rights (HR) Directorate to develop a HR training plan with NMI for Legal Advisors. |  | Fourth Meeting 2023 | A-5 Gundy |  |  | Must include analysis of modern courses to attract young people to work the legal aspect of HR and International Humanitarian Law.
[8 empty] | 2) Electronic Soldier Card and e-learning package |  | CRC FEB 24 CRC MAR 24 | A-5 Gundy | 2024-03-24 |  | NMI are developing an e-learning package for IHL/HR and ROE and producing an electronic version of the Soldier Card for personal mobile phones.
[8 empty] | 3) The Legal Departement ensures that human rights and International Humanitarian Law (IHL) is worked into all MOD strategic documents, and reflected in all educational activities. |  | CRC FEB 24 | A-5 Gundy | 2024-02-24 |  | The Legal Departement opens awareness sessions for leaders and commanders for three days a month - to include Service Commands. Plan must be submitted at coming CRC.
LTO 17 | Protection of civilians | A-4 Grisnich | CHOD office & MACP & M5 & HRD | Two strategies were written, one by M5 and it does not fit with NATO requirements and the other was written by the NATO mission and all the objectives included in the strategy of M5 were included | Work is currently underway to develop observations by the weapons commanders and directorates concerned with the supervision of the Engineering Support Department and the Army Chief of Staff to follow up on completing all observations The request for obtaining the strategy for the protection of civilians issued by the Prime Minister was requested by the National Security Advisory. The NATO Mission Advisor, Ms. Easter, held more than 40 workshops for all arms commanders and various directorates and collected all the observations | NMI advisor and CHOD office working togeather to make this happened | Both strategies are presented in a workshop to come up with a reliable, elaborate and approved strategy | M5 and MACP must develop and have Protection of Civilians Strategy approved by CHOD. | There is a need to follow up on the Soldier Card process. | JAP Review JAN24 CRC JUN24 | A-4 Grisnich | 2024-01-24 |  | M5 to do workshop and present objectives for inclusion in the POC strategy. A second workshop may then be held at the Center for Strategic Studies and Research to review the draft strategy. Our liaison officer with NMI (Admiral Omar Jassim) will coordinate the aforementioned workshops and inform all concerned parties to attend.
LTO 18 | Language Proficiency | A-4 Nowers | DCOS Training & DLI | Many teachers were sent for the purpose of developing their performance in addition to developing curricula and the work of weapons commanders in order to develop the capabilities of the affiliates in the field of English language | Work is continuing at all levels to promote the development of the English language among the ministry's civilian and military employees. | Continue to follow up with the procedures of the Training Department and the Military Language Institute in order to improve the performance of associates in the field of English language | NMI & DCOS training & DLI comes with one plan on page | DCOS TRNG / DUFMS and DLI to develop plans for enhanced English skills in all MOD departements and at Service Commands. | Work is on-going. Must follow-up with the Training Departement and DUFMS. | CRC FEB 24 CRC MAR 24 | A-4 Nowers | 2024-03-24 |  | Initial election of English teachers and reviewing courses in the Annual Training Bulletin (ATB). Service Commands must define their requirements.
LTO 19 | Interoperability with NATO / OCC | A-5 De Vries | CHOD office & SF & GF & DCOS Training | TheOCC working team from CHOD office and DCOS Training was appointed to supervise the allocation of a company from SFD, and in the initial stage of selecting personnel for the company and waiting for approvals. the basic planning team conducted many workshops and conferences in addition to participating in the development of capabilities in various NATO institutions to start the program. | The OCC is ongoing work by the mission advisor with the work team from the ministry and progress slowly but with deliberate steps | Providing support to all teams working in both axes and supporting the NATO mission advisor in addition to the need to appoint an officer from the Army Chief of Staff to be an observer of the basic planning team and we suggest that Major General Pilot Salim Abdul Hamid | We wrote memo to the CHOD for sign the letter to SECUR | DCOS TRNG must facilitate the Core Planning Team (CPT) activities to align to NATO exercise standards. | M5 supports CPT activities and develops war gaming scenarios for the CPT process. | Seventh meeting 2023 CRC FEB 24 | A-5 De Vries | 2024-02-24 | On-going | MoD COS officer (MG Pilot Salim) is allocated to monitor activties. A Special Forces COY is subject to CPT efforts.
LTO 19 | Interoperability with NATO / CPT | A-5 De Vries | SC & DCOS Training | CPT is ongoing in progress . The team in the plan moving forward. | CPT Work continuity and the participation of some team members in the Eager Lion exercise in Jordan to be part of the planning team for the exercise will give great momentum and experience in the field of exercise planning | The letter is sign by the CHOD and given to the NMI COM. We are waiting for the answer of SECUR.
LTO 20 | Readiness | A-5 Mardari | Commission of Rediness | The goal is new and needs to activate both sides from the ministry and the mission side | A plan of action has been drawn up, but there are reports that should | We need to inform the NATO Mission in Iraq to provide us with the best ways to view readiness and how to view reports | NMI follow up with Readiness Commission | The Readiness Commsion elects, prepares and qualifies officers at MOD for Readiness efforts. | Newly initiated LTO - is still immature. Need to develop plan (PoaP) for this LTO. | CRC FEB 24 | A-5 Mardari | 2024-02-24
LTO 21 | Media Strategy | MCiv-6 Bisoffi | DIR of Media & Moral | Work is underway between the Mission and the Directorate of Information for the purpose of developing a working mechanism to formulate a solid media strategy that meets the requirements of the Ministry of Defence | The NATO mission in Iraq has submitted an annual work plan with the Directorate of Information and is in the process of discussion and follow-up. | Continue working with everyone as the goal is new and work at its beginning |  | DIR of Media & Moral Guidance prepares a Media Strategy. | New LTO. NMI advisor and interlocutor develops the plan (PoaP). | COM/CHOD 10 FEB 24 CRC FEB 24 | MCiv-6 Bisoffi | 2024-02-24 |  | A committee will be formed by the GENSEC and the DIR M&MG and representatives from DG Defence Policy and Requirements, M5, DCOS and M2 to support Strategy work..
Service Commands | [7 empty] | 1) Service Commands (SC) must develop a 5-year plan for development of weapon systems (doctrinal) according to the Defence Planning Guide. |  | JAP Review JAN24 | Service Command advisors. | 2024-01-24 |  | Adherence to the Defence Planning Guide and according to four scenarios of the Military Strategy.. Development of a five-year plan to be approved by CHOD.
[8 empty] | 2) Service Commands must develop and implement SC Military Strategies. |  | CRC MAR 24 CRC JUN24 | Service Command advisors. | 2024-03-24 |  | SC Strategies developed of MOD Military Strategy. Aligned to LTO1 Strategy implementation and LTO 2 Defence Planning efforts. All service commands shall form a joint committee under the chairmanship of the Deputy Commander of the relevant Service Command and shall include representatives of M5, Directorate General Defense Approach and Requirements, MoD HQ, and other relevant entities.
[8 empty] | 3) Service Commands implement Job Descriptions as tasked by M9. |  | CRC MAR 24 | Service Command advisors. | 2024-03-24 |  | Coordinated with LTO 3 HRM efforts.
[8 empty] | 4) Service Commands, M9 and the HR Directorate must re-organize and develop their plans to establish Women's Empowerment personnel / teams within Service Commands. |  | CRC MAR 24 | Service Command advisors. | 2024-03-24 |  | Brief at next CRC.
[8 empty] | 5) Service Commands coordinate with M7 to establish priorities for repairs, servicing and maintenance of simulators. |  | CRC MAR 24 | Service Command advisors. | 2024-03-24 |  | (M7) is awaiting a report about shortage of qualified tactical aviation in Army Aviation (?) instructors. This report is to be briefed at the next CRC.
? | [7 empty] | DCOS TRNG leads a committee to contact all Service Commands to align the Military Strategy. |  | JAP Review JAN24 | ED / SC ADV | 2024-01-24 |  | ?